## Color
PROJECT: StreamList app
EZTechMovie |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Christopher Carson, Chad Grismore, Travis Simmons, Victor Ledezma
Project start date: | 2025-05-13 |  |  |  |  | May | [20 empty] | June
Scrolling increment: | 1 |  |  |  |  | 2025-05-14 | 2025-05-15 | 2025-05-16 | 2025-05-17 | 2025-05-18 | 2025-05-19 | 2025-05-20 | 2025-05-21 | 2025-05-22 | 2025-05-23 | 2025-05-24 | 2025-05-25 | 2025-05-26 | 2025-05-27 | 2025-05-28 | 2025-05-29 | 2025-05-30 | 2025-05-31 | 2025-06-01 | 2025-06-02 | 2025-06-03 | 2025-06-04 | 2025-06-05 | 2025-06-06 | 2025-06-07 | 2025-06-08 | 2025-06-09 | 2025-06-10 | 2025-06-11 | 2025-06-12 | 2025-06-13 | 2025-06-14 | 2025-06-15 | 2025-06-16 | 2025-06-17 | 2025-06-18 | 2025-06-19 | 2025-06-20
Project Task | Category | Assigned to | Progress | Start | Days | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F
Software Requirements Specification | On Track | Team | 100% | 2025-05-13 | 5
Wireframe Design | On Track | Team | 100% | 2025-05-20 | 5
Backend Setup | On Track | Team | 100% | 2025-05-27 | 21
Add Subscription Cart | On Track | Team | 100% | 2025-05-27 | 5
OAuth Login Setup | On Track | Team | 100% | 2025-06-03 | 3
Credit CArd Form w/ local Storage | On Track | Team | 100% | 2025-06-05 | 4
Testing | On Track | Team | 100% | 2025-06-09 | 1
Debugging | On Track | Team | 100% | 2025-06-09 | 2
Retesting | On Track | Team | 50% | 2025-06-11 | 1
Deployment | On Track | Team | 0% | 2025-06-16 | 1